LYRA Company Formation & Shareholder Roadmap A Step-by-Step Plan for Incorporating and Structuring LYRA Pty Ltd Prepared: 26 May 2026

| 80% YOU — Founder & Director | 20% ADVISOR — Shareholder |
| --- | --- |

EXECUTIVE SUMMARY This roadmap covers every step to transform LYRA from a sole-trader or personal project into a properly incorporated Australian private company (Pty Ltd) with two shareholders — you (80%) and your advisor (20%). It is structured in four phases: Pre-Incorporation Preparation, Legal Incorporation & IP Assignment, Shareholder & Governance Setup, and Post-Incorporation Compliance. Follow the phases in order. Engage a qualified accountant and solicitor at the appropriate steps — those moments are clearly flagged.

## How to Use This Document

- Work through each Phase in order — later phases depend on earlier ones being complete.

- ⚖️  Legal/Accounting:  Items marked

- ✅  Action Required:  Items marked

- 💡  Tip:  Items marked

Costs shown are indicative for Queensland, Australia as at 2025–2026 and will vary.

| PHASE 1 Pre-Incorporation Preparation | ⏱ Weeks 1–4 |
| --- | --- |

Before lodging anything with ASIC or signing legal documents, you need to make key decisions and get organised. Mistakes made here are expensive to fix later.

## 1.1  Choose Your Company Name

- Decide on the exact company name — most founders use "LYRA Pty Ltd" or a holding variant such as "LYRA Technology Pty Ltd".

- Search ASIC's free name availability register at asic.gov.au to confirm the name is available.

- Search IP Australia's trade mark database (ipaustralia.gov.au) to ensure no conflicting marks exist.

- Check that the matching .com.au and .com domains are available (even if you already have them).

- Reserve the name via ASIC if you are not incorporating immediately (costs ~$52 for 2 months).

💡 Tip You can incorporate with one name and trade under a different business name — but having the trade mark and company name aligned is cleanest and reduces confusion for investors.

## 1.2  Confirm Your Company Structure

- LYRA will be incorporated as a Proprietary Limited company (Pty Ltd) — the standard vehicle for Australian startups.

- It will be a private company (not listed) — no public offer of shares.

| Feature | Detail |
| --- | --- |
| Company Type | Proprietary Limited (Pty Ltd) |
| Shareholders | 2 at incorporation — You (80%) and Advisor (20%) |
| Directors | At minimum: You as sole director and company secretary, or appoint a separate secretary |
| Share Class | Ordinary shares (one class to start — simple and investor-friendly) |
| Total Shares Issued | Recommend 10,000,000 ordinary shares at $0.0001 each (see 1.3) |
| Registered Office | Must be a physical Australian address — your home address or accountant's office is fine |
| Principal Place of Business | Queensland, Australia |

## 1.3  Decide on Share Numbers & Valuation

One of the most important early decisions. Choosing a large share pool now makes future dilution (for investors, employees, option holders) much cleaner.

Recommended Starting Share Structure Issue 10,000,000 ordinary shares at $0.0001 each (total paid-up capital = $1,000). You receive: 8,000,000 shares (80%) Advisor receives: 2,000,000 shares (20%) This leaves room to later create an Employee Share Option Plan (ESOP) or issue shares to future investors without needing to subdivide shares.

- The $0.0001 price per share is for initial capitalisation only — this is not a valuation of LYRA itself.

- The actual value of LYRA as a business will be determined separately (e.g. via a Discounted Cash Flow or revenue multiple) when you raise external capital.

- If the advisor has already contributed value (advisory services, introductions, capital), consider whether their shares should be "paid up" or issued for services rendered — your accountant can advise on tax implications under Division 83A of the ITAA 1997.

## 1.4  Obtain Tax File Number & ABN

- The new company will need its own ABN (Australian Business Number) — apply via abr.gov.au at no cost. This is different from your personal ABN.

- The company will also need its own Tax File Number (TFN) — apply via the ATO or through your accountant.

- Register for GST if you expect annual revenue to exceed $75,000 (or do it at incorporation if you expect to hit this quickly).

- If you will pay yourself or staff a salary, register for PAYG Withholding.

⚖️ Accounting Advice Required Engage a registered tax agent or accountant before incorporation to structure the company correctly for tax purposes — particularly regarding any existing IP transfers, the CGT (capital gains tax) implications of transferring LYRA's IP into the new company, and the small business entity concessions available to you.

## 1.5  Prepare Your Advisor Agreement Terms

Before incorporating, agree in writing (even informally) on the key terms of your advisor's 20% stake to avoid disputes later:

| Term | Decision Required |
| --- | --- |
| Vesting Schedule | Are the advisor's 20% shares fully vested on day one, or subject to a vesting schedule? (e.g. 2-year vest with 6-month cliff) |
| Reverse Vesting / Buyback | If the advisor stops contributing, can the company buy back unvested shares at cost? |
| Consideration | What are the shares issued for? (Advisory services, introductions, mentoring, capital contribution?) Document this clearly. |
| Restrictions on Transfer | Can the advisor sell their shares to anyone? Or are there pre-emption rights (right of first refusal) in favour of you? |
| Tag-Along Rights | If you sell your shares, can the advisor also sell their shares proportionately? |
| Drag-Along Rights | If you accept an offer for 100% of the company, can you compel the advisor to sell their shares too? |
| Non-Compete / Non-Solicit | Is the advisor bound not to compete or poach staff for a period? |
| Board Seat | Does the advisor's 20% entitle them to a board seat / director role? (Typically not automatic at 20%) |

| PHASE 2 Legal Incorporation & IP Assignment | ⏱ Weeks 3–6 |
| --- | --- |

## 2.1  Engage a Commercial Solicitor

While you can incorporate via ASIC directly or through an online service (e.g. Cleardocs, LegalVision), a solicitor is strongly recommended to:

- Draft a bespoke Constitution (not just the replaceable rules),

- Prepare the Shareholders' Agreement between you and your advisor,

- Handle the IP Assignment Deed (transferring LYRA's IP from you personally into the company),

- Issue compliant share certificates and maintain the ASIC register, and

- Advise on any regulatory issues specific to LYRA's technology (AI, data privacy, etc.).

⚖️ Cost Estimate Solicitor fees for a full incorporation package including Constitution, Shareholders' Agreement and IP Assignment typically range from $3,000 to $8,000 + GST for a Queensland technology startup. Shop around — many tech-focused law firms offer fixed-fee startup packages.

## 2.2  Lodge the Company with ASIC

This is the formal step of creating the legal entity. Your solicitor or accountant will typically do this on your behalf via ASIC's online portal.

| What's Needed | Detail |
| --- | --- |
| Company Name | Your chosen name (confirmed available in Step 1.1) |
| Registered Office Address | A physical Queensland address — not a PO Box |
| Director Details | Full legal name, date of birth, residential address, and consent to act as director |
| Company Secretary | Required if you have 2+ directors; optional for a sole director Pty Ltd |
| Share Structure | Number of shares, class, and issue price (see Step 1.3) |
| Constitution | Either the Corporations Act replaceable rules or a bespoke constitution (strongly recommend bespoke) |
| ASIC Filing Fee | ~$597 (2025 rate) for proprietary company registration |

Upon successful lodgement, ASIC will issue:

- An ACN (Australian Company Number) — a unique 9-digit number that permanently identifies the company,

- A certificate of registration (now issued as an email/PDF confirmation), and

- Confirmation of the company's registered details on the ASIC register.

## 2.3  Draft and Adopt the Company Constitution

The Constitution is the company's rulebook. Unlike replaceable rules (which are generic), a bespoke constitution tailored to LYRA should include:

- Share classes and the rights attaching to ordinary shares (voting, dividends, winding up),

- Drag-along and tag-along rights,

- Pre-emption rights on share transfers (right of first refusal),

- Board composition and meeting procedures,

- Decision-making thresholds for reserved matters (matters requiring shareholder approval, e.g. issuing new shares, winding up, changing the business),

- Dividend policy provisions, and

- Dispute resolution mechanism between shareholders.

💡 Tip The Constitution and the Shareholders' Agreement work together. The Constitution is a public document (registered with ASIC); the Shareholders' Agreement is private. Put commercially sensitive provisions (e.g. vesting schedules, specific exit rights) in the Shareholders' Agreement, not the Constitution.

## 2.4  Execute the Shareholders' Agreement

This is the most important legal document between you and your advisor. At a minimum, it should cover:

- Share ownership (80% / 20% split, confirmed),

- Vesting schedule for the advisor's shares (if any),

- Compulsory transfer events (death, insolvency, cessation of advisory role),

- Pre-emption rights on share transfers,

- Drag-along and tag-along rights,

- Reserved matters requiring unanimous or supermajority shareholder approval,

- Deadlock resolution provisions,

- Confidentiality and IP obligations of the advisor,

- Non-compete and non-solicitation,

- Dividend policy (e.g. when dividends may be declared), and

- Exit provisions (trade sale, IPO, share buy-back).

⚖️ Legal Advice Required Both parties should receive independent legal advice before signing the Shareholders' Agreement. While this adds cost, it protects both parties and significantly reduces the risk of the agreement being challenged later.

## 2.5  IP Assignment — Transfer LYRA into the Company

This is one of the most critical and most commonly overlooked steps. LYRA currently belongs to you personally. You must formally transfer it to the new company.

What Must Be Assigned? • All source code, software, and firmware (copyright assignment) • All AI/ML models, training data, and datasets • All domain names and website content • Trade marks (registered and unregistered) and business names • Patent applications (if any) • Confidential information, trade secrets, and know-how • Any contracts (customer, supplier, contractor) — these need novation or assignment with third party consent

- Execute a formal IP Assignment Deed between you (as assignor) and the company (as assignee). This must be in writing and signed by both parties (noting the company will need a director to sign on its behalf — that's you).

- The consideration for the IP assignment should be agreed carefully. Options include: a nominal amount ($1), a loan from the company back to you, or an issue of shares. Each has different tax consequences.

- Tax Warning: The transfer of IP into a company can trigger Capital Gains Tax (CGT) under the ITAA 1997. However, the small business CGT concessions (Subdivision 152) and the rollover provisions (Subdivision 122-A) may significantly reduce or defer any tax. This MUST be reviewed by your accountant before the assignment is executed.

- If LYRA involves code written by contractors or other contributors, ensure those contributors have already signed IP Assignment / Work for Hire agreements transferring their contributions to you — before you assign to the company.

## 2.6  Issue Shares and Prepare Share Register

Once the company is incorporated and the IP is assigned:

- Pass resolutions of the board (you as sole director) to issue shares as per the agreed structure.

- Issue share certificates to each shareholder (you and your advisor).

- Establish and maintain the company's share register — a legal requirement under s.168 of the Corporations Act 2001 (Cth).

- Notify ASIC of any changes to officeholders or share structure within 28 days via Form 484.

| Shareholder | Shares Issued |
| --- | --- |
| You (Founder) | 8,000,000 ordinary shares (80%) |
| Advisor | 2,000,000 ordinary shares (20%) |
| TOTAL | 10,000,000 ordinary shares |

| PHASE 3 Governance, Banking & Operations | ⏱ Weeks 5–8 |
| --- | --- |

## 3.1  Open a Company Bank Account

- Open a dedicated business bank account in the company's name (not your personal account).

- Good options for Australian startups include: ANZ, NAB, CommBank, Macquarie, or neobanks like Zeller or Airwallex for lower fees.

- You will need the ACN, TFN, and proof of incorporation to open the account.

- Ensure the account requires your signature (as sole director) to authorise transactions — or set up appropriate dual-authority controls if you appoint a company secretary later.

- Separate all personal and company finances from day one — this is critical for tax, liability protection, and investor due diligence.

## 3.2  Set Up Accounting & Bookkeeping

- Engage an accountant familiar with technology startups in Queensland (not just a general bookkeeper).

- Set up cloud accounting software: Xero or MYOB are the most common in Australia. Xero integrates well with many startup tools.

- Establish a chart of accounts appropriate for a SaaS/AI company.

- Ensure all IP-related costs (development, subscriptions, contractors) are correctly categorised — this affects your R&D Tax Incentive claims.

💡 R&D Tax Incentive If LYRA involves genuine R&D activities (developing new AI models, experimenting with novel approaches, etc.), the company may be eligible for the Australian Government's R&D Tax Incentive — a 43.5% refundable tax offset for companies with turnover under $20M. Register your R&D activities with AusIndustry within 10 months of the end of your company's first income year. This can be a significant source of non-dilutive cash for a pre-revenue startup.

## 3.3  Establish Governance Documents & Processes

- Hold (and minute) the first formal meeting of directors — even though it's just you. Minutes are a legal requirement.

- Adopt the company's Constitution by board resolution.

- Appoint an auditor if required (generally not required for small Pty Ltd companies).

- Establish a Minute Book — a record of all director and shareholder resolutions. This can be a digital folder but must be maintained.

- Set up a document management system for all company records — contracts, IP assignments, board minutes, share register, tax filings, etc.

## 3.4  Advisor Engagement — Formalise the Relationship

Your advisor wears two hats: shareholder and advisor. Both relationships should be documented separately.

- Advisor Agreement: A separate document (distinct from the Shareholders' Agreement) setting out what the advisor will do for the company, how often you will meet, what resources the company will provide, and any fees or expense reimbursements.

- If the advisor is also a contractor providing services, a separate Services Agreement should be executed.

- Ensure the advisor has signed the company's standard Confidentiality & IP assignment clauses (they likely saw the NDA already — but the company versions of these documents are separate).

## 3.5  Protect LYRA's Intellectual Property

| IP Type | Action Required |
| --- | --- |
| Business Name | Register 'LYRA' as a business name with ASIC ($42 for 1 year / $98 for 3 years) if trading under that name |
| Trade Mark | File a trade mark application with IP Australia for 'LYRA' in the relevant Nice Classes (e.g. Class 42 — Software, Class 35 — Business Services). Cost: ~$250 per class online. Engage a trade mark attorney for a comprehensive search first. |
| Domain Names | Ensure company owns lyraonline.ai and any relevant variants — transfer to company if currently in your name |
| Copyright | Copyright in software and content is automatic in Australia under the Copyright Act 1968 (Cth) — but ensure all code ownership is documented via IP Assignment |
| Patents | If LYRA has novel, non-obvious technical innovations, consider a provisional patent application with IP Australia (~$110 provisional) within 12 months of first use. Engage a patent attorney. |
| Confidentiality | Ensure all contractors, employees, and advisors have signed NDAs (you have the template from LYRA's NDA already) |

## 3.6  Set Up an Employee Share Option Plan (ESOP) — Optional but Recommended

If you plan to hire staff and attract talent with equity, establish an ESOP pool now — before any external investors come in (they will require it anyway).

- Typical startup ESOP pool: 10%–15% of shares on a fully diluted basis.

- If you want a 10% ESOP pool, you could issue a total of 11,111,111 shares (so 10,000,000 + 1,111,111 = 11,111,111 total, with 1,111,111 reserved for the ESOP = ~10%).

- Alternatively, simply carve out the pool from your 80% now — your call, but investors generally prefer the pool to be created before their investment (so it doesn't dilute them).

- The ESOP must be approved by shareholders and comply with the employee share scheme provisions in Division 83A of the ITAA 1997 — your accountant and solicitor must assist.

| POngoing Compliance & Growth Preparation | ⏱ Months 2–12+ |
| --- | --- |

## 4.1  ASIC Annual Compliance

- Annual Review: ASIC sends an annual company statement each year on the anniversary of incorporation. Review and pay the annual review fee (~$310 for a small Pty Ltd, 2025 rates).

- Update ASIC within 28 days of any change to: registered office address, directors, company secretary, or share structure (via Form 484).

- Maintain the company register (share register, option register if applicable, officer register).

## 4.2  Tax Obligations

| Obligation | Timing |
| --- | --- |
| Company Income Tax Return | Annually — due 28 February following the income year end (31 October if lodged by a tax agent) |
| GST / BAS | Quarterly (or monthly if turnover > $20M) — due 28 days after quarter end |
| PAYG Withholding | If paying yourself or staff a salary — withheld each pay period and remitted to ATO quarterly |
| Superannuation | If you pay yourself as an employee: 11.5% (FY25) superannuation guarantee, due 28 days after each quarter |
| Payroll Tax (QLD) | If total Australian wages exceed $1.3M/year — register with Queensland Revenue Office. Not relevant until significant scale. |
| R&D Tax Incentive | Register within 10 months of income year end via business.gov.au / AusIndustry if conducting eligible R&D |
| Fringe Benefits Tax | Relevant if the company provides non-cash benefits (e.g. car, laptop) — FBT year runs 1 April to 31 March |

## 4.3  When Revenue Starts Flowing — Key Decisions

Once LYRA begins generating revenue, you face a series of important decisions:

Director's Salary vs. Dividends

- You can pay yourself a director's salary (deductible to the company, assessable to you as income) or declare dividends from post-tax profits.

- A hybrid approach is often most tax-effective — a modest salary (to access personal tax-free threshold, Medicare levy, and super contributions) plus dividends for distributions of profit.

- Dividends from a company with a 25% tax rate can be franked at 25%, meaning shareholders receive a franking credit that reduces their personal tax.

- Get your accountant to model the optimal split based on your personal income situation.

When and How to Pay Your Advisor's Dividends

- The advisor, as a 20% ordinary shareholder, is entitled to 20% of any dividend declared on ordinary shares — unless the Constitution or Shareholders' Agreement provides otherwise.

- Dividend franking: ensure the company maintains a franking account and attaches franking credits where possible.

- If you want flexibility to pay different amounts to different shareholders (e.g. only pay yourself), you would need a separate share class for the advisor (e.g. "A Class" shares) — discuss with your accountant whether this is worthwhile.

Consider a Discretionary Trust (for You)

- Many founders hold their shares in a discretionary trust ("family trust") rather than personally — this provides income splitting opportunities with family members, CGT discount on exit, and asset protection.

- If you want to restructure from holding shares personally to holding them via a trust, this is significantly easier to do before any external investors come in — or even before you start generating revenue.

- This is a complex area — speak to your accountant before making any changes.

## 4.4  Preparing for External Investment

When LYRA is ready to raise external capital (angel, venture, or strategic), investors will conduct due diligence. Here's what you need to have clean and ready:

| Due Diligence Item | Status Target |
| --- | --- |
| ASIC Register | Up to date — correct officers, share register, registered address |
| Shareholders' Agreement | Executed, current, and includes standard investor-friendly provisions |
| IP Ownership | All IP clearly assigned to the company — no personal ownership of company IP |
| Contractor Agreements | All past and present contractors have signed IP Assignment and Confidentiality agreements |
| Financial Records | Clean, up-to-date accounts prepared by a qualified accountant |
| Tax Compliance | All returns lodged, no outstanding ATO debts or ASIC penalties |
| ESOP | Established, documented, and compliant with Division 83A |
| Cap Table | A clear, accurate capitalisation table showing all shareholders and options |
| Data Privacy | Privacy Policy published; Privacy Act compliance reviewed (especially if LYRA handles personal data) |
| Terms of Service | Up to date and reviewed by a solicitor |
| Trade Mark | Filed or registered in key jurisdictions |

💡 Tip — Build a Data Room Start building a virtual data room (e.g. a structured Google Drive or Notion workspace) from day one. Keep all company documents, contracts, financial statements, IP records, and product documentation in one organised location. When investors ask for due diligence materials, you will be able to respond in hours rather than weeks — which signals professionalism and speeds up funding rounds.

## 4.5  Governance Maturity as You Grow

As the company grows, your governance practices should grow with it:

| Stage | Governance Actions |
| --- | --- |
| Pre-Revenue | Sole director, no formal board meetings required — but keep minutes of key resolutions |
| Early Revenue ($0–$500K ARR) | Hold quarterly board meetings (even informally), produce management accounts monthly, engage external accountant |
| Growth ($500K–$2M ARR) | Consider adding an independent non-executive director, formalise board cadence, prepare audited financial statements |
| Scale ($2M+ ARR or post-Series A) | Full board with independent directors, audit committee, formal reporting to shareholders, legal and financial advisors on retainer |

MASTER CHECKLIST

Use this checklist to track your progress:

| Task | Status |
| --- | --- |
| Confirm company name availability (ASIC + IP Australia) | ☐ Not Started |
| Agree share structure (10M shares, 80/20 split) | ☐ Not Started |
| Agree advisor vesting / transfer terms | ☐ Not Started |
| Engage commercial solicitor | ☐ Not Started |
| Engage startup accountant | ☐ Not Started |
| Incorporate company with ASIC | ☐ Not Started |
| Adopt bespoke Constitution | ☐ Not Started |
| Execute Shareholders' Agreement | ☐ Not Started |
| Execute IP Assignment Deed | ☐ Not Started |
| Issue shares & update share register | ☐ Not Started |
| Obtain company ABN and TFN | ☐ Not Started |
| Register for GST (if applicable) | ☐ Not Started |
| Open company bank account | ☐ Not Started |
| Set up accounting software (Xero/MYOB) | ☐ Not Started |
| File first board minutes | ☐ Not Started |
| Register LYRA trade mark with IP Australia | ☐ Not Started |
| Register LYRA business name with ASIC | ☐ Not Started |
| Transfer domain names to company | ☐ Not Started |
| Establish ESOP (optional — recommended) | ☐ Not Started |
| Register R&D activities with AusIndustry (if eligible) | ☐ Not Started |
| Build virtual data room for investor due diligence | ☐ Not Started |
| Review Privacy Policy and Terms of Service | ☐ Not Started |

## Indicative Cost Summary (Queensland, 2025–2026)

| Item | Estimated Cost (AUD) |
| --- | --- |
| ASIC Company Registration | ~$597 |
| Solicitor — Incorporation Package (Constitution, SHA, IP Assignment) | $3,000 – $8,000 + GST |
| Accountant — Structural Advice & Tax Planning | $1,000 – $3,000 + GST |
| Trade Mark Application (1 class) | ~$250 per class (DIY) / $1,500–$3,000+ with attorney |
| Business Name Registration (3 years) | ~$98 |
| Xero Accounting Software (annual) | ~$660 – $1,320/year |
| ASIC Annual Review Fee (Pty Ltd) | ~$310/year |
| TOTAL SETUP ESTIMATE | $5,000 – $14,000 (one-off) + ~$1,000/year ongoing |

IMPORTANT DISCLAIMER This document is a general information guide only. It does not constitute legal, accounting, tax, or financial advice. Laws, fees, and regulations change frequently. You must engage qualified Australian legal and accounting professionals before incorporating a company, transferring intellectual property, issuing shares, or entering into any shareholder agreement. The author accepts no liability for decisions made in reliance on this document.